## 01 28 23 InflightStatus
Project # | Technology | Project | Stakeholder | Last Update | Last Update Date | Priority | Revised Estimated Comp Qtr/Date | BTD Team | BTD Team Lead | Contractors | Business Unit | Phase | % Comp | Records
ACCT-Blue Chip | ACCT | Increment 2: Loan Level Accounting | Todd Wallace | 1/27: Subservicing Fee Expense: Tables have been produced: - Kicked off allocations discussions with Holli and her team Supplemental File - Data Table created: Gfee Wire, ADF pipeline, Subservicing fee. Development of stored procedures & ADF pipleins is in progress. | 2027-01-01 | 1 | Q1-2023 (Feb) | Data Delivery & Analytics | Jorge Arias | Sandeep Kosuri, Athanasios Gavatides, Vasu Babu, Suresh Pasupuleti, Srinath Jagarlamudi | Finance | DEV | 85% | 1
COLL-Blue Chip | COLL | Consolidated Life of Loan Collateral Management Process Enhancements: Breakdown in Phases by Business Group: (Phase 1: Transaction Management, Phase 2: Pingora, Phase 3: EBO, Phse 4: Collateral Management) | Richard Jolis | 1/27: Established weekly status update starting 1/30 with Richard & Julio. Decison made to concurrently fast track capturing & doument "as-is" current state business processes. The first deliverale is to complete the end-to-end workflow and prpcess steps with: Transaction Management & the Denver Group) Brian Vanscoy), Pingora (BU Leader: Jenn Jackson, SME: Brigitte Gross), Originations (BU Leader: Donna Harkness, SME: Casey Boutcher, Robert Klein), EBO (BU Leader: Donna Gross, SME: Faizah Khan), Collateral (BU Leader: Mary Schroeder, SME: Kathleen Aquino) | 2027-01-01 | 1 | Q1-2023 (March) | Data Delivery & Analytics | Pablo Valle | Keerthana Muralikrishna, Srinath Jagarlamudi, Yonathan Aseffa | MSR General Operations | Requirements | 3% | 1
AZURE-Blue Chip | AZURE | LakeView MSR Azure Cloud Migration PoC to compare financial models run performance between on-prem and Azure cloud for research team. | Carlos Cortinas | 1/27: Completed hardware inventory. Working with MSR team to understand the process model. Plan to install Azure Migration tool on-prem. | 2027-01-01 | 1 | Q1-2023 (February) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
AZURE-DECOM | AZURE | Build SFTP Azure Cloud Solution for all of our source file vendors ( LVDMS Servicers, EBO banks, and LHIS vendors ) | Carlos Cortinas | 1/27: Collaborating with the EBO Vendor to start testing the PoC | 2027-01-01 | 2 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | Servicers Dependency | 10% | 1
Azure-TRAN | Azure | Transition Azure LakeView subscription from BAM IT to MSR BTD | Carlos Cortinas | 1/27: WIP to remove non lakeview users | 2027-01-01 | 3 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
AZURE-REFACTOR | AZURE | Refactoring LogicApp to .Net based APIs | Carlos Cortinas | 1/27: PoC 80% completed | 2027-01-01 | 3 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
AZURE-SECURITY | AZURE | Transition and co-monitoring Azure activities with ReliaQuest. Provide access to ReliaQuest and setup GreyMatter connections | Carlos Cortinas | 1/27: 15% completed. Continuation efforts to collaborate with Pending ReliaQuest | 2027-01-01 | 1 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
AZURE-SECURITY | AZURE | DigitalEra findings and remediation | Carlos Cortinas | 1/27: 10% completed. Continuation efforts to collaborate with DigitalEro Group to schedule followup workshop meetings with BAM-IT. | 2027-01-01 | 1 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
AZURE-DECOM | AZURE | Decomission unencrypted PII Servicer.SSN fields and MERs SSNs | Carlos Cortinas | 1/27: 80% comleted. | 2027-01-01 | 2 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
AZURE-OPTIM | AZURE | Azure Database Performance Tuning to improve daily load processing time: 1. Performance tuning - Remove redundant and unused indexes. 2. Enable Secoundary Replica | Carlos Cortinas | 1/27: BAM-IT redundant list is completed. Pending ARB review and approval | 2027-01-01 | 2 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
AZURE-CLEANUP | AZURE | Azure Storage Accounts 1. Clean up not used and machine generated Azure Storage Accounts 2. Categorize Hot/Archive/Cold Stroage Accounts | Carlos Cortinas | 1/27: Completed the storage inventory. | 2027-01-01 | 2 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
AZURE-OPTIMIZE | AZURE | ADF Improvements to apply better exception handling, alerts and notifications | Carlos Cortinas | 1/27: Researching solutions. Pending ARB review | 2027-01-01 | 2 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
AZURE-COST | AZURE | Develop a consolidate Azure Monitoring Dashboard to include Performance, Security, and Cost | Carlos Cortinas | 1/27: 10% completed. | 2027-01-01 | 2 | Q1-2023 (March) | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1 | 9.6154
AZURE-MICROSOFT | AZURE | Azure Best Practice to enable and create policies that can help us to enforce security, cost and access baselines | Carlos Cortinas | 1/27: Pending approval | 2027-01-01 | 3 | Q2-2023 | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | DEV | 10% | 1
MSR-APPL-REPORTS | MSR | Servicers Reporting | Bryan Pommer | 1/27: Follow-up demo is planned (date tbd) to review content reuirements in order to complete UI & reporting development. The sites have been created and permissions assigned as requested to start development. Reference URLs below to start development. • Lakeview ActiveView: https://bayview0.sharepoint.com/sites/LVAV o LoanCare: https://bayview0.sharepoint.com/sites/LVAV/LoanCare/ o MTB: https://bayview0.sharepoint.com/sites/LVAV/MTB/ o Flagstar: https://bayview0.sharepoint.com/sites/LVAV/Flagstar/ o Mr Cooper: https://bayview0.sharepoint.com/sites/LVAV/MrCooper/ o ServiceMac: https://bayview0.sharepoint.com/sites/LVAV/ServiceMac/ | 2027-01-01 | 1 | Q1-2023 (Feb) | Data Operations | Michelle Bevins | Lori Brown, Durga Maank | Lakeview MSR Portfolio - Servicers | DEV | 55% | 1
MSR-APPL-WORKFLOW | MSR | Loan Oversight Workflow Management Tool | Frank Ruhl | 1/27: Continuation of business requirements and distribution to secure signoff. The following business stakeholders/SMEs have been identified: Geoff Hynes, Justin tucker, Colleen Reynolds, Vinny Viespoli | 2027-01-01 | 2 | Q1-2023 (March) | Data Delivery & Analytics | Pablo Valle | Keerthana Muralikrishna, Srinath Jagarlamudi, Yonathan Aseffa | Lakeview MSR Portfolio - Collateral Management | Discovery | 5% | 1
HELPDESK-SVCNOW | HELPDESK | Lakeview Assist/Leveraging SN Application | Carlos Cortinas | 1/27: BAM-IT negotiations with ServiceNow to reduce oaverall subscription costs. Target date to complete is 2nd week in December. Dependecny is on BAM-ITfinalizing the current ServiceNow MSA for Bayview and to confirm that a seperate instance can be implemened without incurring additional licenses. Emron is following-up and a decision to proceed, where LV will have the opportunity to tailor a seperate instance to leveage and manage SN features and functionality. | 2027-01-01 | 1 | Q1-2023 (Jan) | Release Management & QA | Sara Eeday | Navya Sree | Lakeview LVDMS - Release Management | Requirements | 5% | 1
ORIGIN-APPL-REPORTS | ORIGIN | Servicers Complaint Reports. | Carole Kriete | 1/27: Continuation of meetings to finalize business, technical, final design and reporting requirements. | 2027-01-01 | 1 | Q1-2023 | Data Operations | Michele Ross | Suresh Pasupuleti, Durga Maank | CLS Compliance: Originations | DEV | 45% | 1
ORIGIN-APPL-TICKET | ORIGIN | Servicers Ticketing Solution | Carole Kriete | 1/27: Continuation of meetings to finalize business, technical, final design and reporting requirements. | 2027-01-01 | 1 | Q1-2023 (Feb) | Data Operations | Michelle Bevins | Lori Brown | CLS Compliance: Originations | DEV | 45% | 1

## ProdSupp_Enhancements
BTD Support & Maintenance Project - 2023 |  | Filter |  | Graph
Production Project Number | Project | Stakeholder | BTD Team | BTD Team Manager/Lead | Contractor | Business Unit | Phase | Records
1 | LVDMS, Servicers & Data Delivery | Bryan Pommer | Data Operations | Michelle Bevins | Rajeev Ratna, Navya Sree, Sai Krishna, Pradeep Sathi | MSR Portfolio | Production | 1
2 | LVDMS, Servicers, Data Delivery: Dependency Business Units (Originations, LHIS, Collateral management) | Bryan Pommer | Data Operations | Michelle Bevins | Rajeev Ratna, Navya Sree, Sai Krishna, Sai Krishna | Originations | Production | 1
3 | LHIS Carriers API, Pre Quote Runs & Marketing | Arturo Perez | Data Operations | Cybil Joseph | Jeswanth Kumar, Navya Sree, Sai Krishna | Lakeview Household Insurance | Production | 1
4 | LHIS Marketing & External Data Vendor Integration | Karmi Van Wyk | Data Operations | Cybil Joseph | Poonam Gupta, Vasu Babu, Jeswanth Dowpati | Lakeview Household Insurance | Production | 1
5 | MERS Reconciliation | Linda Baboun | Data Architecture & Development | Cybil Joseph | Poonam Gupta , Vasu Babu, Navya Sree | MERS Compliance | Production | 1
6 | EBO, Kairos, Defect Management & Collateral Management | Donna Gross | Data Governance & Security | Jorge Arias | Sandeep Kosuri, Athanasios Gavatides, Chetu, Vasu Babu, Navya Sree, Sai Krishna | EBO | Production | 1
7 | Phase 1: Enterprise Security Improvements | Carlos Cortinas | Data Architecture & Development | Cindy Liu | Shruki Abdulahi, Kevin Gonzalez, Humbert Hernandez | MSR Portfolio | Production | 1
8 | Vendor: (OvalEdge) Data Governance | Carlos Cortinas | Data Governance & Security | Jesus Brito | Keerthana Muralikrishnan, Lakshminarayana Nethi | MSR Portfolio | Production | 1
9 | Vendor: (QRM) EBO & Originations | Donna Gross | Data Infrastructure & Cloud Operations | Cindy Liu | Kevin Gonzalez, Humbert Hernandez, Joseph Bernal | EBO | Production | 1
10 | Phase 1: Loan Level Accounting | Todd Wallace | Data Operations | Jorge Arias | Athanasios Gavatides, Suresh Pasupuleti, Srinath Jagarlamudi, Navya Sree, Pradeep Sathi | Finance | Production | 1
11 | Refactoring of LHIS Carriers Data Integration to Azure (Stillwater, Safeco, Travelers, Heritage, Towerhill, Hippo). | Arturo Perez | Data Infrastructure & Cloud Operations | Cybil Joseph | Poonam Gupta, Vasu Babu, Jeswanth Dowpati | Lakeview Household Insurance | Production | 1
12 | Decomission of MS Access Databases | Colleen Reynolds | Data Architecture & Development | Jesus Brito | Poonam Gupta | Oversight Loss Analysis, Lakeview Subservicer Oversight | Production | 1
13 | Decommission of Originations Oneview | Karmi Van Wyk | Data Operations | Michelle Bevins | Manasa Reddy | Lakeview Household Insurance | Production | 1
14 | (EOT) RPA Projects using Microsoft Power Automate Tool | Carlos Cortinas | Data Delivery & Analytics | Pablo Valle | Jeswanth Dowpati, Humbert Hernandez | EBO | Production | 1
15 | Refactor Production Tidal Jobs with Microsoft Power Automate | Carlos Cortinas | Data Infrastructure & Cloud Operations | Kevin Gonzalez | Jeswanth Dowpati, Sandeep Kosuri, Jeswanth Dowpati | MSR Portfolio | Production | 1
16 | PII Cleanup | Bryan Pommer | Data Governance & Security | Eli Perez | Data Stewards (No follow-up support) | MSR Portfolio | Production | 1
17 | Increment 1: Loan Level Monthly Tables | Todd Wallace | Data Delivery & Analytics | Jorge Arias | Sandeep Kosuri, Athanasios Gavatides, Suresh Pasupuleti, Navya Sree, Pradeep Sathi | Finance | Production | 1
18 | Phase 2: Loanview (Version 1.5) | Bryan Pommer | Data Operations | Michelle Bevins | Manasa Reedy, Chetu, Navya Sree | MSR Portfolio | Production | 1
19 | LVDMS Azure Cloud Migration | Carlos Cortinas | Data Architecture & Development | Cindy Liu | Kevin Gonzalez, Shruki Abdulahi, Humbert Hernandez, Pradeep Sathi | MSR Portfolio | Production | 1
20 | Power BI Data Analytics & Self Servicing | Carlos Cortinas | Data Delivery & Analytics | Pablo Valle | Durga Maank, Jeswant Dowpati | MSR Portfolio | Production | 1
21 | Rearchitect the Daily Servicers Load Dashboard | Carlos Cortinas | Data Operations | Michelle Bevins | Durga Maank | MSR Portfolio | Production | 1
23 | Rearchitect MERS Reconciliation & Annual Audit Application | Linda Baboun | Data Delivery & Analytics | Cybil Joseph | Durga Maank, Jeswant Dowpati | MERS Compliance | Production | 1
24 | Help Desk: Lakeview MSR Portfoio & Dependency Business Operations | Carlos Cortinas | Data Delivery & Analytics | Pablo Valle | Kevin Gonzalez, Humbert Hernandez, Sandeep Kosuri, Sai Krishna | Lakeview Help Desk | Production | 1
25 | KNOCK Monitoring & WAT Team: Tidal Jobs, ADF Processes: On/Offshore (Applications, Data Feeds/Delivery & Cyclic Jobs Monitoring etc) | Carlos Cortinas | Data Delivery & Analytics | Pablo Valle | Kevin Gonzalez, Humbert Hernandez, Sandeep Kosuri, Sai Krishna | Lakeview Help Desk | Production | 1
22 | Phase 1: Lakeview MO365 Subscription Azure User Security and leverage Microsoft and AirGap enterprise solution. | Carlos Cortinas | Data Infrastructure & Cloud Operations | Eli Perez | Joe Bernal, Kevin Gonzalez, Humbert Hernandez | Glasslake Canada | Production | 1

## LV2023 Backlog
BTD Back-Log Projects |  | Filter
Backlog Number | Project | Stakeholder | Requested Date | Reference | Priority | Business Group | Status2 | Records
1 | Vendor Integration: Equifax (Pending in/Out Scope from Bryan P | Bryan Pommer | 2022-08-01 | Meeting | Tbd | MSR Portfolio | Pending Project Brief, Scope Requirements & approval to proceed. | 1
2 | LHIS: Solution: Citrix > Download Data > Store in Azure DB. Time: Q2-2023 | Dave Silverberg | 2022-09-01 | Meeting | Tbd | LHIS | Pending Project Brief, Scope Requirements & approval to proceed. | 1
3 | Enterprise Finance Projects | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
4 | Lakeview/MSR Fund Cost Analysis and Rationalization | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
5 | Liquidity Framework / Project Plan for New Agency requirements | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
6 | Lakeview MSR and Advance Financing | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
7 | Tax/swaps | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
8 | Treasury | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
9 | Earnings Analysis | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
10 | Advance Analysis | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
11 | Org Development | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
12 | Controllership | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
13 | Pingora Initiatives | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
14 | Reporting | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
15 | Internal Audit. Engagement 2023 Plan | Todd Wallace | 2023-01-01 | email | Tbd | Finance | Pending Project Brief, Scope Requirements & approval to proceed. | 1
16 | Originations: QRM Consolidation | Joel Goldman | 2023-01-01 | Carlos Cortinas | Tbd | Originations | Pending Project Brief, Scope Requirements & approval to proceed. | 1
17 | Originations: Data Governance | Joel Goldman | 2023-01-01 | Carlos Cortinas | Tbd | Originations | Pending Project Brief, Scope Requirements & approval to proceed. | 1
18 | Originations: Power BI Collaboration | Joel Goldman | 2023-01-01 | Carlos Cortinas | Tbd | Originations | Pending Project Brief, Scope Requirements & approval to proceed. | 1
19 | Originations: Decommission of On-Prem LVDMS | Joel Goldman | 2023-01-01 | Carlos Cortinas | Tbd | Originations | Pending Project Brief, Scope Requirements & approval to proceed. | 1

## 2022 Closed Projects
BTD Closed Projects - 2023 |  | Filter
Original Project Number | Project | Stakeholder | Business Unit | Status | Records
4 - Closed | Decomission of MS Access Databases | Colleen Reynolds | Oversight Loss Analysis, Lakeview Subservicer Oversight | Support, Maintenance & Enhancements | 1
5 - Closed | Decommission of Originations Oneview | Arturo Perez | Lakeview Household Insurance | Support, Maintenance & Enhancements | 1
14 - Closed | PII Cleanup | Bryan Pommer | Lakeview MSR Portfolio - PII Security | Support, Maintenance & Enhancements | 1
15 - Closed | Increment 1: Loan Level Monthly Tables | Todd Wallace | Lakeview MSR Portfolio - Data Operations | Support, Maintenance & Enhancements | 1
16 - Closed | Phase 2: Loanview (Version 1.5) | Bryan Pommer | Lakeview MSR Portfolio - Data Operations | Support, Maintenance & Enhancements | 1
17 - Closed | LVDMS Azure Cloud Migration | Carlos Cortinas | Lakeview LVDMS - Azure Cloud | Support, Maintenance & Enhancements | 1
18 - Closed | Power BI Data Analytics & Self Servicing | Carlos Cortinas | Lakeview LVDMS - Data Analytics | Support, Maintenance & Enhancements | 1
25 - Closed | (Completed) Rearchitect the Daily Servicers Load Dashboard | Carlos Cortinas | Lakeview MSR Portfolio - LVDMS | Support, Maintenance & Enhancements | 1
28 -Closed | Phase 1: Lakeview MO365 Subscription Azure User Security and leverage Microsoft and AirGap enterprise solution. | Carlos Cortinas | Lakeview Household Insurance | Support, Maintenance & Enhancements | 1